## tasks
Epic # | Story # | Task # | Summary | Phase/Env | Assignee | Due Date | State | Description | Estimate | Comments
KDM-1171 |  | - | KDM Release 2.2 |  | gusevdmi
| KDM-1172 | - | IMPL -> KDM Release 2.2 |  | gusevdmi
|  | KDM-1326 | [MILESTONE]: requirements signoff for KDM Release 2.2 |  | plu |  |  | MILESTONE
|  | KDM-1327 | [MILESTONE]: requirements analysis freeze for KDM Release 2.2 |  | plu |  |  | MILESTONE
|  | KDM-1328 | [MILESTONE]: development freeze for KDM Release 2.2 |  | gusevdmi |  |  | MILESTONE
|  | KDM-1329 | [MILESTONE]: unit testing freeze for KDM Release 2.2 |  | bhusare |  |  | MILESTONE
|  | KDM-1330 | [MILESTONE]: completion of [IMPL] phase for KDM Release 2.2 |  | gusevdmi |  |  | MILESTONE
| KDM-1173 | - | INIT -> KDM Release 2.2 |  | gusevdmi
|  | KDM-1331 | Prepare high level release plan for KDM 2.2 | INIT | gusevdmi
|  | !!! | Create/open CRQ for KDM Release 2.2 | INIT | makarana
|  | ??? | Create general testing strategy for KDM Release 2.2 | INIT | mrazj
|  | KDM-1332 | Deploy software on DEV environment and check it's readiness | INIT | kamenskl
|  |  | > Deploy PDC Metadata (DL + TD) on DEV and check readiness for release |  | kuco
|  |  | > Deploy DL part on DEV/check readiness for release |  | kuco
|  |  | > Deploy TD scripts (Stage/Views/DataMart) on DEV/check readiness for release |  | swiernia
|  |  | > Ingest KDM data end-2-end on DEV env |  | kuco
|  |  | > Create/review TPT scripts for SPs |  | kuco
|  | KDM-1180 | Create/review testing inputs for SDLC (QAP and DTP) | INIT | bhusare
|  | KDM-1333 | Create/review KDM 2.2 Design Spec | INIT | gusevdmi
|  | KDM-1177 | Execute unit tests on DEV and provide results | INIT | bhusare
|  | KDM-1334 | Create release branch for KDM 2.2 Release | INIT | kamenskl
|  | KDM-1179 | Create code review doc and provide it to Confluence | INIT | bhusare
|  | KDM-1335 | [MILESTONE]: code freeze for KDM Release 2.2 | INIT | kamenskl |  |  | MILESTONE
|  | KDM-1336 | [MILESTONE]: completion of INIT phase for KDM Release 2.2 | INIT | gusevdmi |  |  | MILESTONE
| KDM-1174 | - | SIT -> KDM Release 2.2 |  | gusevdmi
|  | KDM-1337 | Route CRQ for initial approvals (SME approvals) | SIT | makarana
|  | KDM-1138 | Prepare (create/update) release branches/artifacts/packages for DL | SIT | bobekmi
|  | KDM-1178 | Create/update test strategy/cases/scenarios for SIT and put scenarios to ALM | SIT | bhusare
|  | KDM-1339 | Upload documents into MIDAS and get approvals | SIT | makarana
|  | KDM-1181 | Get tests cases pre-approvals in ALM for SIT (SIT pre-approve) | SIT | bhusare
|  | KDM-1340 | Deploy software on SIT environment and check it's readiness | SIT | kuco
|  |  | > Deploy Informatica on SIT and check readiness |  |  |  |  | No Informatica deployment for this release :)
|  |  | > Deploy PDC Metadata for TD (IDW Engine) on SIT and check readiness |  | kuco
|  |  | > Deploy DL part (pipelines) on SIT and check readiness |  | bobekmi
|  |  | > Create TD Datamart deployment package |  | kuco
|  |  | > Deploy TD Datamart deployment package on SIT and check readiness |  | kuco
|  |  | > Populate TD data structures on SIT with metadata (if necessary) |  | kuco
|  | KDM-1341 | Ingest data end-2-end on SIT environment (by PDC) | SIT | kuco
|  | KDM-1183 | Execute tests scenarios for SIT (do SIT for Release 2.2) | SIT | bhusare
|  | KDM-1184 | Get tests cases post-approvals in ALM for SIT (SIT post-approve) | SIT | bhusare
|  | KDM-1185 | Create DSR (Development Summary Report) | SIT | bhusare
|  | KDM-1342 | Put DSR to Midas and get it approved | SIT | makarana
|  | KDM-1343 | [MILESTONE]: completion of [SIT] phase for KDM Release 2.2 | SIT | bhusare |  |  | MILESTONE
| KDM-1175 | - | UAT -> KDM Release 2.2 |  | gusevdmi
|  | KDM-1344 | Create/update tests cases/scenarios for UAT and put to ALM | UAT | plu
|  | KDM-1345 | Create/update IQOQ scenarios and put to ALM | UAT | bhusare
|  | KDM-1346 | Get test cases pre-approvals in ALM for UAT (UAT pre-approve) | UAT | plu
|  | KDM-1189 | Get IQOQ pre-approvals in ALM for UAT (IQOQ pre-approve) | UAT | bhusare |  |  | !!!
|  | KDM-1348 | Request dedicated support from external teams for UAT/PROD | UAT | gusevdmi |  |  | Email all external teams and KDM Team about UAT/PROD timelines and request (dedicated) support. External Teams: Ingest Team (maybe +Ada Team), Teradata Team, Informatica Team, Core Team, (optional) BD Platform Team.
|  | KDM-1349 | Deploy software on UAT environment and check it's readiness | UAT | kuco
|  |  | > Deploy Informatica on UAT and check readiness |  | lenkerr |  |  | No Informatica deployment for this release :)
|  |  | > Deploy PDC Metadata for TD (IDW Engine) on UAT and check readiness |  | kuco
|  |  | > Deploy DL part (pipelines) on UAT and check readiness |  | kuco
|  |  | > Deploy TD Datamart deployment package on UAT and check readiness |  | kuco
|  |  | > Populate TD data structures on UAT with metadata (if necessary) |  | kuco
|  | KDM-1350 | Ingest data end-2-end on UAT environment (by PDC) | UAT | kuco
|  | KDM-1187 | Execute IQOQ for UAT and get post-approvals | UAT | bhusare
|  | KDM-1351 | Execute tests scenarios for UAT (do UAT for Release 2.2) | UAT | plu
|  | KDM-1352 | Get tests cases post-approvals in ALM for UAT (UAT post-approve) | UAT | plu
|  | KDM-1353 | [MILESTONE]: completion of [UAT] phase for KDM Release [#] | UAT | plu |  |  | MILESTONE
| KDM-1176 | - | PROD -> KDM Release 2.2 |  | gusevdmi
|  | KDM-1354 | Get CRQ Implementation approval | PROD | makarana
|  | KDM-1355 | Deploy software on PROD environment and check it's readiness | PROD | kuco
|  |  | > Deploy Informatica on PROD and check readiness |  |  |  |  | No Informatica deployment for this release :)
> Deploy PDC Metadata for TD (IDW Engine) on PROD and check readiness
|  |  | > Deploy DL part (pipelines) on PROD and check readiness |  | bobekmi
|  |  | > Deploy TD Datamart deployment package on PROD and check readiness |  | kuco |  |  | Provide deployment package to Teradata team and assure deployment.
|  |  | > Populate TD data structures on PROD with metadata (if necessary) |  | kuco
|  | KDM-1356 | Ingest data end-2-end on PROD environment (by PDC) | PROD
|  | KDM-1188 | Execute IQOQ for PROD and get post-approvals | PROD | bhusare
|  | KDM-1357 | Connect KDM Dashboard to Back-End on PROD | PROD | milotova |  |  | Dashboard may be already connected. Check it works.
|  | KDM-1358 | Get SDLC Approval for Release 2.2 (if necessary) | PROD | neelamag
|  | KDM-1359 | Communicate KDM Release 2.2 to end users | PROD | neelamag
|  | KDM-1360 | Close CRQ for Release 2.2 | PROD | makarana
|  | KDM-1361 | [MILESTONE]: completion of [PROD] phase for KDM Release 2.2 | PROD/Go Live! | plu |  |  | MILESTONE
|  | KDM-1362 | [MILESTONE]: completion of [Go Live!] phase for KDM Release 2.2 | PROD/Go Live! | plu |  |  | MILESTONE

## config
#release | 2.0