## tasks
Epic # | Story # | Task # | Summary | Phase/Env | Assignee | Due Date | State | Description | Estimate | Comments
KDM-1207 |  | - | KDM Release 2.1.1 |  | gusevdmi
| KDM-1208 | - | IMPL -> KDM Release [#] |  | gusevdmi
|  | KDM-1245 | [MILESTONE]: requirements signoff for KDM Release 2.1.1 | IMPL | gusevdmi |  |  | MILESTONE
|  | KDM-1246 | [MILESTONE]: requirements analysis freeze for KDM Release 2.1.1 | IMPL | gusevdmi |  |  | MILESTONE
|  | KDM-1247 | [MILESTONE]: development freeze for KDM Release 2.1.1 | IMPL | gusevdmi |  |  | MILESTONE
|  | KDM-1248 | [MILESTONE]: unit testing freeze for KDM Release 2.1.1 | IMPL | gusevdmi |  |  | MILESTONE
|  | KDM-1249 | [MILESTONE]: completion of [IMPL] phase for KDM Release 2.1.1 | IMPL | gusevdmi |  |  | MILESTONE
| KDM-1209 | - | INIT -> KDM Release [#] |  | gusevdmi
|  | KDM-1250 | Prepare high level release plan for KDM 2.1.1 | INIT | gusevdmi |  |  |  | 2 | Usually it's a list of Jira tasks and short plan in Confluence with names of responsible persons.
|  | KDM-1227 | Create/open CRQ for KDM Release 2.1.1 | INIT | makarana
|  | KDM-1213 | Create/review/update Requirements Specifications | INIT | makarana
|  | KDM-1215 | Create/update/review QAP, DSR and QASR | INIT | chittik
|  | KDM-1238 | Review/update SDLC Documentation for 2.1.1 | INIT | makarana
|  | KDM-1252 | Create general testing strategy for KDM Release 2.1.1 | INIT | bhusare
|  | KDM-1253 | Deploy software on DEV environment and check it's readiness | INIT | kamenskl |  |  |  | 1 | This deployment is just a preparation for real release - check readiness. It doesn't require to create any kind of packages/artfacts.
|  |  | > Deploy PDC Metadata (DL + TD) on DEV and check readiness for release |  | kuco |  |  |  | n/a
|  |  | > Deploy DL part on DEV\check readiness for release |  | kuco |  |  |  | n/a
|  |  | > Deploy TD scripts (Stage\Views\DataMart) on DEV\check readiness for release |  | swiernia |  |  |  | n/a
|  |  | > Ingest KDM data end-2-end on DEV env |  | kuco |  |  |  | n/a
|  |  | > Create\review TPT scripts for SPs |  | kuco |  |  |  | n/a
|  | KDM-1217 | Create/review testing inputs for SDLC (QAP and DTP) | INIT | bhusare
|  | KDM-1214 | Create/review Design Spec and describe the changes to this release | INIT | makarana
|  | KDM-1254 | Execute unit tests on DEV and provide results | INIT | bhusare
|  | KDM-1255 | Create release branch for KDM 2.1.1 Release | INIT | kamenskl
|  | KDM-1256 | Create code review doc and provide it to Confluence | INIT | bhusare
|  | KDM-1257 | [MILESTONE]: code freeze for KDM Release 2.1.1 | INIT | gusevdmi |  |  | MILESTONE | 0
|  | KDM-1258 | [MILESTONE]: completion of INIT phase for KDM Release 2.1.1 | INIT | gusevdmi |  |  | MILESTONE | 0
| KDM-1210 | - | SIT -> KDM Release [#] |  | gusevdmi
|  | KDM-1259 | Route CRQ for initial approvals (SME approvals) | SIT | makarana |  |  |  | 1
|  | KDM-1260 | Prepare (create/update) release branches/artifacts/packages for DL | SIT | bobekmi |  |  |  | 2 | Probably it worth to create subtasks for this task
|  | KDM-1216 | Create/update test strategy/cases/scenarios for SIT and put scenarios to ALM | SIT | bhusare
|  | KDM-1261 | Upload documents into MIDAS and get approvals | SIT | makarana
|  | KDM-1218 | Get tests cases pre-approvals in ALM for SIT (SIT pre-approve) | SIT | bhusare
|  | KDM-1262 | Deploy software on SIT environment and check it's readiness | SIT | kuco
|  |  | > Deploy PDC Metadata for TD (IDW Engine) on SIT and check readiness |  | kuco |  |  |  | n/a
|  |  | > Deploy DL part (pipelines) on SIT and check readiness |  | bobekmi |  |  |  | n/a
|  |  | > Create TD Datamart deployment package |  | kuco |  |  |  | n/a
|  |  | > Deploy TD Datamart deployment package on SIT and check readiness |  | kuco |  |  |  | n/a
|  |  | > Populate TD data structures on SIT with metadata (if necessary) |  | kuco |  |  |  | n/a
|  | KDM-1263 | Ingest data end-2-end on SIT environment (by PDC) | SIT | kuco |  |  |  |  | Link from this task to task "Prepare source files...". Same for UAT/PROD.
|  | KDM-1219 | Execute tests scenarios for SIT (perform SIT) | SIT | bhusare |  |  |  | 4
|  | KDM-1220 | Get tests cases post-approvals in ALM for SIT (SIT post-approve) | SIT | bhusare |  |  |  | 0.5
|  | KDM-1264 | Create DSR (Development Summary Report) | SIT | bhusare
|  | KDM-1265 | Put DSR to Midas and get it approved | SIT | makarana
|  | KDM-1266 | [MILESTONE]: completion of [SIT] phase for KDM Release 2.1.1 | SIT | gusevdmi |  |  | MILESTONE | 0
| KDM-1211 | - | UAT -> KDM Release [#] |  | gusevdmi
|  | KDM-1267 | Create/update tests cases/scenarios for UAT and put to ALM | UAT | bhusare
|  | KDM-1268 | Create/update IQOQ scenarios and put to ALM | UAT | bhusare
|  | KDM-1269 | Get test cases pre-approvals in ALM for UAT (UAT pre-approve) | UAT | bhusare
|  | KDM-1223 | Get IQOQ pre-approvals in ALM for UAT (IQOQ pre-approve) | UAT | bhusare
|  | KDM-1270 | Request dedicated support from external teams for UAT/PROD | UAT | gusevdmi |  |  | Email all external teams and KDM Team about UAT/PROD timelines and request (dedicated) support. External Teams: Ingest Team (maybe +Ada Team), Teradata Team, Informatica Team, Core Team, (optional) BD Platform Team. | 0.5
|  | KDM-1271 | Deploy software on UAT environment and check it's readiness | UAT | kuco
|  |  | > Deploy PDC Metadata for TD (IDW Engine) on UAT and check readiness |  | kuco |  |  |  | n/a
|  |  | > Deploy DL part (pipelines) on UAT and check readiness |  | kuco |  |  |  | n/a
|  |  | > Deploy TD Datamart deployment package on UAT and check readiness |  | kuco |  |  | Provide deployment package to Teradata team and assure deployment. | n/a
|  |  | > Populate TD data structures on UAT with metadata (if necessary) |  | kuco |  |  |  | n/a
|  | KDM-1273 | Ingest data end-2-end on UAT environment (by PDC) | UAT | kuco
|  | KDM-1221 | Execute IQOQ for UAT and get post-approvals | UAT | bhusare
|  | KDM-1274 | Execute tests scenarios for UAT (do UAT for Release 2.1.1) | UAT | neelamag
|  | KDM-1275 | Get tests cases post-approvals in ALM for UAT (UAT post-approve) | UAT | bhusare
|  | KDM-1277 | [MILESTONE]: completion of [UAT] phase for KDM Release [#] | UAT | gusevdmi |  |  | MILESTONE | 0
| KDM-1212 | - | PROD -> KDM Release 2.0 |  | gusevdmi
|  | KDM-1278 | Get CRQ Implementation approval | PROD | makarana
|  | KDM-1279 | Deploy software on PROD environment and check it's readiness | PROD | kuco
|  |  | > Deploy PDC Metadata for TD (IDW Engine) on PROD and check readiness |  | budka |  |  |  | n/a
|  |  | > Deploy DL part (pipelines) on PROD and check readiness |  | bobekmi |  |  |  | n/a
|  |  | > Deploy TD Datamart deployment package on PROD and check readiness |  | kuco |  |  | Provide deployment package to Teradata team and assure deployment. | n/a
|  |  | > Populate TD data structures on PROD with metadata (if necessary) |  | kuco |  |  |  | n/a
|  | KDM-1280 | Ingest data end-2-end on PROD environment (by PDC) | PROD | budka
|  | KDM-1222 | Execute IQOQ for PROD and get post-approvals | PROD | bhusare
|  | KDM-1281 | Connect KDM Dashboard to Back-End on PROD | PROD | milotova |  |  | Dashboard may be already connected. Check it works.
|  | KDM-1282 | Get SDLC Approval for Release 2.1.1 (if necessary) | PROD | neelamag
|  | KDM-1283 | Communicate KDM Release 2.1.1 to end users | PROD | neelamag
|  | KDM-1284 | Close CRQ for Release 2.1.1 | PROD | makarana
|  | KDM-1285 | [MILESTONE]: completion of [PROD] phase for KDM Release 2.1.1 | PROD/Go Live! | gusevdmi |  |  | MILESTONE | 0
|  | KDM-1286 | [MILESTONE]: completion of [Go Live!] phase for KDM Release 2.1.1 | PROD/Go Live! | gusevdmi |  |  | MILESTONE | 0

## config
#release | 2.0