## KDM Release Tasks
Tasks/Sub-Tasks | Phase/Env | Assignee | Due Date | Description | Estimate | Comments
Prepare high level plan and schedule for Release [#] | INIT | Dmitrii Gusev |  |  |  | Usually it's a list of Jira tasks and short plan in Confluence with names of responsible persons.
Create/open CRQ for Release [#] | INIT | Dmitrii Gusev | 06.09.2018
> Create CRQ Draft (in Confluence and Remedy) |  | Dmitrii Gusev |  |  | n/a
> Ask for CRQ review |  | Dmitrii Gusev |  |  | n/a
> Add high level tech overview |  | ??? |  |  | n/a
> Add high level testing overview |  | Jaroslav Mraz |  |  | n/a
Create general testing strategy for Release [#] | INIT | Jaroslav Mraz |  | Create general testing strategy according release scope and put it to Confluence.
Do Impact Analysis for Release [#] | INIT | Dmitrii Gusev | 07.09.2018 | Analyze scope of upcoming release and analyze impact on different parts of KDM software solution (Informatica, DL, TD, others). As a result of Impact analysis - clear state which artifacts should be used for DL Pipelines (previous releases/new generated, re-creation status of data structures (DL/TD), other technical things. | 4 | It worth to create sub-tasks for team members to participate.
Deploy software on DEV environment and check it's readiness | INIT | Dmitrii Gusev |  | Deployment of software solution on DEV environment in order to check release readiness. | 1 | This deployment is just a preparation for real release - check readiness. It doesn't require to create any kind of packages/artfacts.
> Deploy Informatica on DEV and check readiness for release |  | Pavel Jaromersky |  |  | n/a
> Deploy PDC Metadata (DL + TD) on DEV and check readiness for release |  | Jaroslav Kuco
> Deploy DL part on DEV/check readiness for release |  | Jaroslav Kuco
> Prepare TD scripts for release and provide them to [Ingest Team] |  | Lubomir Kamensky |  |  | n/a
> Deploy TD scripts (Stage/Views/DataMart) on DEV/check readiness for release |  | Jaroslav Kuco |  | This task is only for scripts deployment on DEV, it isn't necessary to create TD eployment package. | n/a
> Populate TD data structures on DEV with metadata (if necessary) |  | Pavel Jaromersky |  |  | n/a
Ingest KDM data end-2-end on DEV environment (by PDC) | INIT | Jaroslav Kuco | 07.09.2018 |  | 1
Milestone: code freeze for Release [#] | INIT |  | 07.09.2018 | MILESTONE | 0
Milestone: completion of [INIT] phase for Release [#] | INIT |  | 07.09.2018 | MILESTONE | 0
Route CRQ for initial approvals (SME approvals) | SIT | Dmitrii Gusev |  |  | 1
Prepare (create/update) release branches/artifacts/packages for Release [#] | SIT | Dmitrii Gusev | 07.09.2018 | In order to be able to do KDM 1.1.1 Release (go to SIT/UAT/PROD) KDM Team needs release branch to be created. Please create release branch(es) for DL with version 18.2.3 (if necessary, for release branch(es) use suffix [-KDM] (without square braces) with fixed versions of all used toolset/components. KDM DL pipelines/systems: KDH_GLOBAL, EXM_BI_BIBERACH, EXM_FI_FREDERICK Participants: Motal, Tomas - please approve it; Bobek, Miroslav - please coordinate this activity; Pyayt, Alexander - please do all necessary tech support for it; Kuco, Jaroslav - please go ahead with TD package creation for SIT; Jaromersky, Pavel - please go ahead with Informatica repository release branch (the same name as for DL part) for KDM. |  | Probably it worth to create subtasks for this task
> Approve from TU for branches/artifacts creation |  | Tomas Motal |  | As a TU please approve preparations for KDM SIT for Release [#]. Results of Impact Analysis are attached. | n/a
> Prepare TD scripts for deployment package/check readiness |  | Jaroslav Kuco |  |  | n/a
> Prepare DL (pipelines, necessary configs) for SIT (branches/artifacts) |  | Miroslav Bobek |  |  | n/a
> Update/prepare Informatica workflows for SIT and check readiness |  | Pavel Jaromersky |  |  | n/a
Create/update test strategy/cases/scenarios for SIT and put scenarios to ALM | SIT | Jardo Mraz |  |  |  | Tests Strategy page should be created. Usually we use one page for Strategy and for Impact Analysis - see task for it above.
Create/review/update "Functional and Design Spec" | SIT | Dmitrii Gusev
Upload documents into MIDAS and get approvals | SIT | Katerina Cechalova
Get tests cases pre-approvals in ALM for SIT (SIT pre-approve) | SIT | Jardo Mraz
Prepare source files for data ingestion on SIT | SIT | Dmitrii Gusev | 12.09.2018
Deploy software on SIT environment and check it's readiness | SIT | Dmitrii Gusev | 11.09.2018
> Deploy Informatica on SIT and check readiness |  | Pavel Jaromersky
> Deploy PDC Metadata (DL + TD) on SIT and check readiness |  | Milan Budka
> Deploy DL part (pipelines) on SIT and check readiness |  | Jaroslav Kuco
> Create TD deployment package (Stage + DataMart) |  | Grzegorz Swierniak |  | Participation from Jaro Kuco is needed. Package should be attached to this task.
> Deploy TD deployment package (Stage + DataMart) on SIT and check readiness |  | Jaroslav Kuco |  | Provide package to Teradata Team/deploy by ourself and assure deployment.
> Populate TD data structures on SIT with metadata (if necessary) |  | Pavel Jaromersky
Ingest data end-2-end on SIT environment (by PDC) | SIT | Jaroslav Kuco | 12.09.2018 |  |  | Link from this task to task "Prepare source files...". Same for UAT/PROD.
Execute tests scenarios for SIT (do SIT for Release [#]) | SIT | Jardo Mraz | 14.09.2018 |  | 4
Get tests cases post-approvals in ALM for SIT (SIT post-approve) | SIT | Jardo Mraz | 14.09.2018 |  | 0.5
Milestone: completion of [SIT] phase for Release [#] | SIT |  | 14.09.2018 | MILESTONE | 0
Create/update tests cases/scenarios for UAT and put to ALM | UAT | Satvik/Jaroslav Mraz | 10.09.2018
Create/update IQOQ scenarios and put to ALM | UAT | Jardo Mraz | 10.09.2018
Get test cases pre-approvals in ALM for UAT (UAT pre-approve) | UAT | Jardo Mraz | 17.09.2018
Get IQOQ pre-approvals in ALM for UAT (IQOQ pre-approve) | UAT | Jardo Mraz | 17.09.2018
Prepare source files for data ingestion for UAT | UAT | Dmitrii Gusev
Request dedicated support from external teams for UAT/PROD | UAT | Dmitrii Gusev | 17.09.2018 | Email all external teams and KDM Team about UAT/PROD timelines and request (dedicated) support. External Teams: Ingest Team (maybe +Ada Team), Teradata Team, Informatica Team, Core Team, (optional) BD Platform Team. | 0.5
Deploy software on UAT environment and check it's readiness | UAT | Dmitrii Gusev | 17.09.2018
> Deploy Informatica on UAT and check readiness |  | Pavel Jaromersky
> Deploy PDC Metadata (DL + TD) on UAT and check readiness |  | Milan Budka
> Deploy DL part (pipelines) on UAT and check readiness |  | Jaroslav Kuco
> Deploy TD package (Stage + DataMart) on UAT and check readiness |  | Jaroslav Kuco |  | Provide deployment package to Teradata team and assure deployment.
> Populate TD data structures on UAT with metadata (if necessary) |  | Pavel Jaromersky
Ingest data end-2-end on UAT environment (by PDC) | UAT | Milan Budka | 17.09.2018
Execute IQOQ for UAT and get post-approvals | UAT | Jardo Mraz | 18.09.2018
Execute tests scenarios for UAT (do UAT for Release [#]) | UAT | Satvik/Jaroslav Mraz | 19.09.2018
Get tests cases post-approvals in ALM for UAT (UAT post-approve) | UAT | Satvik/Jaroslav Mraz | 19.09.2018
Milestone: completion of [UAT] phase for Release [#] | UAT |  | 19.09.2019 | MILESTONE | 0
Prepare source files for data ingestion for PROD | PROD | Dmitrii Gusev | 20.09.2018
Get CRQ Implementation approval | PROD | Jiri Janous | 20.09.2018
Deploy software on PROD environment and check it's readiness | PROD | Dmitrii Gusev | 21.09.2018
> Deploy Informatica on PROD and check readiness |  | Pavel Jaromersky
> Deploy PDC Metadata (DL + TD) on PROD and check readiness |  | Milan Budka
> Deploy DL part (pipelines) on PROD and check readiness |  | Jaroslav Kuco
> Deploy TD package (Stage + DataMart) on PROD and check readiness |  | Jaroslav Kuco |  | Provide deployment package to Teradata team and assure deployment.
> Populate TD data structures on PROD with metadata (if necessary) |  | Pavel Jaromersky
Ingest data end-2-end on PROD environment (by PDC) | PROD | Milan Budka | 21.09.2018
Execute IQOQ for PROD and get post-approvals | PROD | Jardo Mraz | 21.09.2018
Connect KDM Dashboard to Back-End on PROD | PROD | Tomas Kissik/Linda | 21.09.2018 | Dashboard may be already connected. Check it works.
Get SDLC Approval for Release [#] (if necessary) | PROD | Jiri Janous | 28.09.2018
Close CRQ for Release [#] | PROD | Dmitrii Gusev | 28.09.2018
Milestone: completion of [PROD] phase for Release [#] | PROD/Go Live! |  | 21.09.2018 | MILESTONE | 0
Milestone: completion of [Go Live!] phase for Release [#] (Dashboard + Back-end) | PROD/Go Live! |  | 21.09.2018 | MILESTONE