## tasks
Epic # | Story # | Task # | Summary | Phase/Env | Assignee | Due Date | State | Description | Estimate | Comments
KDM-741 | - | - | KDM Release [#] |  | gusevdmi | 2018-12-10
| KDM-742 | - | INIT -> KDM Release [#] |  | gusevdmi | 2018-11-23
|  | KDM-857 | Prepare high level release plan for KDM 2.0 | INIT | gusevdmi | 2018-11-21 |  |  | 2 | Usually it's a list of Jira tasks and short plan in Confluence with names of responsible persons.
|  | KDM-858 | Create/open CRQ for KDM Release 2.0 | INIT | makarana
|  | ??? | Create general testing strategy for Release [#] | INIT | mrazj |  |  | Create general testing strategy according release scope and put it to Confluence.
|  | KDM-859 | Deploy software on DEV environment and check it's readiness | INIT | kamenskl | 2018-11-20 |  | Deployment of software solution on DEV environment in order to check release readiness. | 1 | This deployment is just a preparation for real release - check readiness. It doesn't require to create any kind of packages/artfacts.
|  | KDM-860 | > Deploy Informatica on DEV and check readiness for release |  | jaromers |  |  |  | n/a
|  | KDM-864 | > Deploy PDC Metadata (DL + TD) on DEV and check readiness for release |  | kuco |  |  |  | n/a
|  | KDM-863 | > Deploy DL part on DEV/check readiness for release |  | kuco |  |  |  | n/a
|  | KDM-862 | > Deploy TD scripts (Stage/Views/DataMart) on DEV/check readiness for release |  | swiernia |  |  |  | n/a
|  | KDM-865 | > Ingest KDM data end-2-end on DEV env |  | kuco |  |  | This task is only for scripts deployment on DEV, it isn't necessary to create TD eployment package. | n/a
|  | KDM-858 | > Create necessary TPT scripts for new SPs |  | kuco |  |  |  | n/a
|  | KDM-820 | Testing inputs for SDLC (QAP and DTP) | INIT | mrazj
|  | KDM-845 | Create and review KDM 2.0 Design Spec | INIT | gusevdmi
|  | KDM-823 | Create Unit tests for TD Datamart | INIT | mrazj
|  | KDM-856 | Execute unit tests on DEV and provide results | INIT | francmi
|  | KDM-874 | Create release branch for KDM 2.0 Release | INIT | kamenskl
|  | KDM-875 | Create code review doc and provide it to Team | INIT | francmi
| - | KDM-746 | [MILESTONE]: code freeze for KDM Release [#] | INIT | gusevdmi | 2018-11-21 |  | MILESTONE | 0
| - | KDM-747 | [MILESTONE]: completion of INIT phase for KDM Release [#] | INIT | gusevdmi | 2018-11-23 |  | MILESTONE | 0
| KDM-743 |  | SIT -> KDM Release [#]
|  | KDM-873 | Route CRQ for initial approvals (SME approvals) | SIT | makarana |  |  |  | 1
|  | KDM-876 | Prepare (create/update) release branches/artifacts/packages for DL | SIT | bobekmi |  |  |  | 2 | Probably it worth to create subtasks for this task
|  | KDM-872 | Create/update test strategy/cases/scenarios for SIT and put scenarios to ALM | SIT | mrazj |  |  |  |  | Tests Strategy page should be created. Usually we use one page for Strategy and for Impact Analysis - see task for it above.
|  | KDM-811 | > Creating test scenarios - Raw Materials |  | mrazj
|  | KDM-756 | > Creating test scenarios - BioAssay (Dev Labs) |  | mrazj
|  | KDM-827 | > Creating test scenarios - BIB |  | mrazj
|  | ??? | Upload documents into MIDAS and get approvals | SIT | Katerina Cechalova
|  | KDM-880 | Get tests cases pre-approvals in ALM for SIT (SIT pre-approve) | SIT | mrazj
|  | KDM-881 | Deploy software on SIT environment and check it's readiness | SIT | gusevdmi
|  | KDM-882 | > Deploy Informatica on SIT and check readiness |  | lenkerr |  |  |  | n/a
|  | KDM-883 | > Deploy PDC Metadata for TD (IDW Engine) on SIT and check readiness |  | kuco |  |  |  | n/a
|  | KDM-884 | > Deploy DL part (pipelines) on SIT and check readiness |  | kuco |  |  |  | n/a
|  | KDM-885 | > Create TD Datamart deployment package |  | kuco |  |  |  | n/a
|  | KDM-886 | > Deploy TD Datamart deployment package on SIT and check readiness |  | kuco |  |  | Provide package to Teradata Team/deploy by ourself and assure deployment. | n/a
|  | KDM-887 | > Populate TD data structures on SIT with metadata (if necessary) |  | kuco |  |  |  | n/a
|  | KDM-888 | Ingest data end-2-end on SIT environment (by PDC) | SIT | kuco |  |  |  |  | Link from this task to task "Prepare source files...". Same for UAT/PROD.
|  | KDM-889 | Execute tests scenarios for SIT (do SIT for Release 2.0) | SIT | mrazj |  |  |  | 4
|  | KDM-890 | Get tests cases post-approvals in ALM for SIT (SIT post-approve) | SIT | mrazj |  |  |  | 0.5
|  | ??? | Create DSR (Development Summary Report) | SIT | mrazj
|  | ??? | Put DSR to Midas and get it approved | SIT | ???
| - | KDM-748 | [MILESTONE]: completion of SIT phase for KDM Release [#] | SIT | gusevdmi | 2018-11-27 |  | MILESTONE | 0
| KDM-744 |  | UAT -> KDM Release [#]
|  | KDM-891 | Create/update tests cases/scenarios for UAT and put to ALM | UAT | makarana
|  | KDM-892 | Create/update IQOQ scenarios and put to ALM | UAT | mrazj
|  | KDM-893 | Get test cases pre-approvals in ALM for UAT (UAT pre-approve) | UAT | mrazj
|  | KDM-894 | Get IQOQ pre-approvals in ALM for UAT (IQOQ pre-approve) | UAT | mrazj
|  | KDM-895 | Request dedicated support from external teams for UAT/PROD | UAT | gusevdmi |  |  | Email all external teams and KDM Team about UAT/PROD timelines and request (dedicated) support. External Teams: Ingest Team (maybe +Ada Team), Teradata Team, Informatica Team, Core Team, (optional) BD Platform Team. | 0.5
|  | KDM-900 | Deploy software on UAT environment and check it's readiness | UAT | gusevdmi
|  | KDM-901 | > Deploy Informatica on UAT and check readiness |  | lenkerr |  |  |  | n/a
|  | KDM-902 | > Deploy PDC Metadata for TD (IDW Engine) on UAT and check readiness |  | kuco |  |  |  | n/a
|  | KDM-903 | > Deploy DL part (pipelines) on UAT and check readiness |  | kuco |  |  |  | n/a
|  | KDM-905 | > Deploy TD Datamart deployment package on UAT and check readiness |  | kuco |  |  | Provide deployment package to Teradata team and assure deployment. | n/a
|  | KDM-906 | > Populate TD data structures on UAT with metadata (if necessary) |  | kuco |  |  |  | n/a
|  | KDM-896 | Ingest data end-2-end on UAT environment (by PDC) | UAT | kuco
|  | KDM-897 | Execute IQOQ for UAT and get post-approvals | UAT | mrazj
|  | KDM-898 | Execute tests scenarios for UAT (do UAT for Release 2.0) | UAT | ???
|  | KDM-899 | Get tests cases post-approvals in ALM for UAT (UAT post-approve) | UAT | mrazj
| - | KDM-749 | [MILESTONE]: completion of UAT phase for KDM Release [#] | UAT | Dmitrii Gusev | ? |  | MILESTONE | 0
| KDM-745 |  | PROD -> KDM Release 2.0
|  | KDM-915 | Get CRQ Implementation approval | PROD | makarana
|  | KDM-919 | Deploy software on PROD environment and check it's readiness | PROD | gusevdmi
|  | KDM-921 | > Deploy Informatica on PROD and check readiness |  | lenkerr |  |  |  | n/a
|  | KDM-922 | > Deploy PDC Metadata for TD (IDW Engine) on PROD and check readiness |  | Milan Budka ??? |  |  |  | n/a
|  | KDM-923 | > Deploy DL part (pipelines) on PROD and check readiness |  | bobekmi |  |  |  | n/a
|  | KDM-924 | > Deploy TD Datamart deployment package on PROD and check readiness |  | kuco |  |  | Provide deployment package to Teradata team and assure deployment. | n/a
|  | KDM-925 | > Populate TD data structures on PROD with metadata (if necessary) |  | kuco |  |  |  | n/a
|  | KDM-920 | Ingest data end-2-end on PROD environment (by PDC) | PROD | budka
|  | KDM-918 | Execute IQOQ for PROD and get post-approvals | PROD | mrazj
|  | KDM-917 | Connect KDM Dashboard to Back-End on PROD | PROD | milotova |  |  | Dashboard may be already connected. Check it works.
|  | ??? | Get SDLC Approval for Release [#] (if necessary) | PROD | Jiri Janous
|  | KDM-946 | Communicate KDM Release 2.0 to end users | PROD | neelamag
|  | KDM-916 | Close CRQ for Release 2.0 | PROD | makarana
| - | KDM-750 | Milestone: completion of [PROD] phase for Release [#] | PROD/Go Live! | gusevdmi | ? |  | MILESTONE | 0
| - | KDM-751 | Milestone: completion of [Go Live!] phase for Release [#] (Dashboard + Back-end) | PROD/Go Live! | gusevdmi | ? |  | MILESTONE | 0

## config
#release | 2.0