## tasks
Epic # | Story # | Task # | Summary | Phase/Env | Assignee | Due Date | State | Description | Estimate | Comments
KDM-961 | - | - | KDM Release [#] |  | gusevdmi |  | In Progress
| KDM-962 | - | IMPL -> KDM Release [#] |  | gusevdmi |  | Done
| - | KDM-967 | [MILESTONE]: requirements signoff for KDM Release [$release] |  | gusevdmi | 2019-01-22 | Done | MILESTONE
| - | KDM-968 | [MILESTONE]: requirements analysis freeze for KDM Release [$release] |  | gusevdmi | 2019-01-22 | Done | MILESTONE
| - | KDM-969 | [MILESTONE]: development freeze for KDM Release [$release] |  | gusevdmi | 2019-03-04 | Done | MILESTONE
| - | KDM-970 | [MILESTONE]: unit testing freeze for KDM Release [$release] |  | gusevdmi | 2019-03-04 | Done | MILESTONE
| - | KDM-977 | [MILESTONE]: completion of [IMPL] phase for KDM Release [$release] |  | gusevdmi | 2019-03-04 | Done | MILESTONE
| KDM-963 | - | INIT -> KDM Release [#] |  | gusevdmi |  | In Progress
|  | KDM-1018 | Prepare high level release plan for KDM 2.1 | INIT | gusevdmi |  | In Progress |  | 2 | Usually it's a list of Jira tasks and short plan in Confluence with names of responsible persons.
|  | KDM-1004 | Create/open CRQ for KDM Release 2.1 | INIT | makarana |  | In Progress
|  | ??? | Create general testing strategy for KDM Release 2.1 | INIT | mrazj |  |  | Create general testing strategy according release scope and put it to Confluence. Won't be created for KDM 2.1 Release.
|  | KDM-1024 | Deploy software on DEV environment and check it's readiness | INIT | kamenskl |  | In Progress | Deployment of software solution on DEV environment in order to check release readiness. | 1 | This deployment is just a preparation for real release - check readiness. It doesn't require to create any kind of packages/artfacts.
|  | KDM-1025 | > Deploy Informatica on DEV and check readiness for release |  | lenkerr |  | To Do |  | n/a
|  | KDM-1026 | > Deploy PDC Metadata (DL + TD) on DEV and check readiness for release |  | kuco |  | To Do |  | n/a
|  | KDM-1027 | > Deploy DL part on DEV/check readiness for release |  | kuco |  | To Do |  | n/a
|  | KDM-1028 | > Deploy TD scripts (Stage/Views/DataMart) on DEV/check readiness for release |  | swiernia |  | Done |  | n/a
|  | KDM-1029 | > Ingest KDM data end-2-end on DEV env |  | kuco |  | To Do | This task is only for scripts deployment on DEV, it isn't necessary to create TD eployment package. | n/a
|  | KDM-1030 | > Create/review TPT scripts for SPs |  | kuco |  | In Progress |  | n/a
|  | KDM-1022 | Create/review testing inputs for SDLC (QAP and DTP) | INIT | mrazj |  | To Do
|  | KDM-1023 | Create/review KDM 2.1 Design Spec | INIT | gusevdmi |  | In Progress
|  | KDM-1017 | Create unit tests for TD Datamart | INIT | francmi |  | Done
|  | KDM-999 | Execute unit tests on DEV and provide results | INIT | francmi |  | In Progress
|  | KDM-1020 | Create release branch for KDM 2.1 Release | INIT | gusevdmi |  | Done
|  | KDM-1019 | Create code review doc and provide it to Confluence | INIT | francmi |  | To Do
| - | KDM-971 | [MILESTONE]: code freeze for KDM Release 2.1 | INIT | gusevdmi | 2019-03-08 | Done | MILESTONE | 0
| - | KDM-972 | [MILESTONE]: completion of INIT phase for KDM Release 2.1 | INIT | gusevdmi | 2019-03-08 | Done | MILESTONE | 0
| KDM-964 | - | SIT -> KDM Release [#] |  | gusevdmi |  | In Progress
|  | KDM-1021 | Route CRQ for initial approvals (SME approvals) | SIT | makarana |  | In Progress |  | 1
|  | KDM-1032 | Prepare (create/update) release branches/artifacts/packages for DL | SIT | bobekmi |  | To Do |  | 2 | Probably it worth to create subtasks for this task
|  | KDM-1000 | Create/update test strategy/cases/scenarios for SIT and put scenarios to ALM | SIT | mrazj |  | Done |  |  | Tests Strategy page should be created. Usually we use one page for Strategy and for Impact Analysis - see task for it above.
|  | ??? | > Creating test scenarios - Raw Materials |  | mrazj
|  | ??? | > Creating test scenarios - BioAssay (Dev Labs) |  | mrazj
|  | ??? | > Creating test scenarios - BIB |  | mrazj
|  | KDM-1033 | Upload documents into MIDAS and get approvals | SIT | makarana |  | To Do
|  | KDM-1034 | Get tests cases pre-approvals in ALM for SIT (SIT pre-approve) | SIT | mrazj |  | To Do
|  | KDM-1040 | Deploy software on SIT environment and check it's readiness | SIT | kuco |  | To Do
|  | KDM-1041 | > Deploy Informatica on SIT and check readiness |  | lenkerr |  | To Do | No Informatica deployment for this release :) | n/a
|  | KDM-1042 | > Deploy PDC Metadata for TD (IDW Engine) on SIT and check readiness |  | kuco |  | Done |  | n/a
|  | KDM-1043 | > Deploy DL part (pipelines) on SIT and check readiness |  | bobekmi |  | To Do |  | n/a
|  | KDM-1044 | > Create TD Datamart deployment package |  | kuco |  | To Do |  | n/a
|  | KDM-1045 | > Deploy TD Datamart deployment package on SIT and check readiness |  | kuco |  | To Do | Provide package to Teradata Team/deploy by ourself and assure deployment. | n/a
|  | KDM-1046 | > Populate TD data structures on SIT with metadata (if necessary) |  | kuco |  | To Do |  | n/a
|  | KDM-1035 | Ingest data end-2-end on SIT environment (by PDC) | SIT | kuco |  | To Do |  |  | Link from this task to task "Prepare source files...". Same for UAT/PROD.
|  | KDM-1036 | Execute tests scenarios for SIT (do SIT for Release 2.1) | SIT | mrazj |  | To Do |  | 4
|  | KDM-1037 | Get tests cases post-approvals in ALM for SIT (SIT post-approve) | SIT | mrazj |  | To Do |  | 0.5
|  | KDM-1038 | Create DSR (Development Summary Report) | SIT | mrazj |  | To Do
|  | KDM-1039 | Put DSR to Midas and get it approved | SIT | makarana |  | To Do
| - | KDM-973 | [MILESTONE]: completion of [SIT] phase for KDM Release 2.1 | SIT | gusevdmi | 2019-03-15 | To Do | MILESTONE | 0
| KDM-965 | - | UAT -> KDM Release [#] |  | gusevdmi |  | To Do
|  | KDM-1120 | Create/update tests cases/scenarios for UAT and put to ALM | UAT | mrazj
|  | ??? | Create/update IQOQ scenarios and put to ALM | UAT | mrazj |  |  | Done by KDM-1000
|  | KDM-1121 | Get test cases pre-approvals in ALM for UAT (UAT pre-approve) | UAT | mrazj
|  | KDM-1122 | Get IQOQ pre-approvals in ALM for UAT (IQOQ pre-approve) | UAT | mrazj
|  |  | Request dedicated support from external teams for UAT/PROD | UAT | gusevdmi |  |  | Email all external teams and KDM Team about UAT/PROD timelines and request (dedicated) support. External Teams: Ingest Team (maybe +Ada Team), Teradata Team, Informatica Team, Core Team, (optional) BD Platform Team. | 0.5
|  | KDM-1123 | Deploy software on UAT environment and check it's readiness | UAT | kuco
|  | ??? | > Deploy Informatica on UAT and check readiness |  | lenkerr |  |  | No Informatica deployment for this release :) | n/a
|  | KDM-1134 | > Deploy PDC Metadata for TD (IDW Engine) on UAT and check readiness |  | kuco |  |  |  | n/a
|  | KDM-1135 | > Deploy DL part (pipelines) on UAT and check readiness |  | kuco |  |  |  | n/a
|  | KDM-1136 | > Deploy TD Datamart deployment package on UAT and check readiness |  | kuco |  |  | Provide deployment package to Teradata team and assure deployment. | n/a
|  |  | > Populate TD data structures on UAT with metadata (if necessary) |  | kuco |  |  |  | n/a
|  | KDM-1124 | Ingest data end-2-end on UAT environment (by PDC) | UAT | kuco
|  | KDM-1115 | Execute IQOQ for UAT and get post-approvals | UAT | mrazj
|  | KDM-1125 | Execute tests scenarios for UAT (do UAT for Release 2.1) | UAT | ???
|  | KDM-1126 | Get tests cases post-approvals in ALM for UAT (UAT post-approve) | UAT | mrazj
| - | KDM-974 | [MILESTONE]: completion of [UAT] phase for KDM Release [#] | UAT | gusevdmi | 2019-03-22 | To Do | MILESTONE | 0
| KDM-966 | - | PROD -> KDM Release 2.0 |  | gusevdmi |  | To Do
|  | KDM-1127 | Get CRQ Implementation approval | PROD | makarana
|  | KDM-1128 | Deploy software on PROD environment and check it's readiness | PROD | kuco
|  | ??? | > Deploy Informatica on PROD and check readiness |  | lenkerr |  |  | No Informatica deployment for this release :) | n/a
|  | KDM-1138 | > Deploy PDC Metadata for TD (IDW Engine) on PROD and check readiness |  | Milan Budka ??? |  |  |  | n/a
|  | KDM-1139 | > Deploy DL part (pipelines) on PROD and check readiness |  | bobekmi |  |  |  | n/a
|  | KDM-1140 | > Deploy TD Datamart deployment package on PROD and check readiness |  | kuco |  |  | Provide deployment package to Teradata team and assure deployment. | n/a
|  | KDM-1141 | > Populate TD data structures on PROD with metadata (if necessary) |  | kuco |  |  |  | n/a
|  | KDM-1129 | Ingest data end-2-end on PROD environment (by PDC) | PROD | budka
|  | KDM-1116 | Execute IQOQ for PROD and get post-approvals | PROD | mrazj
|  | KDM-1130 | Connect KDM Dashboard to Back-End on PROD | PROD | milotova |  |  | Dashboard may be already connected. Check it works.
|  | KDM-1131 | Get SDLC Approval for Release 2.1 (if necessary) | PROD | neelamag
|  | KDM-1132 | Communicate KDM Release 2.1 to end users | PROD | neelamag
|  | KDM-1133 | Close CRQ for Release 2.1 | PROD | makarana
| - | KDM-975 | [MILESTONE]: completion of [PROD] phase for KDM Release [#] | PROD/Go Live! | gusevdmi | 2019-04-01 | To Do | MILESTONE | 0
| - | KDM-976 | [MILESTONE]: completion of [Go Live!] phase for KDM Release [#] | PROD/Go Live! | gusevdmi | 2019-04-01 | To Do | MILESTONE | 0

## config
#release | 2.0